## Defects
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
1 | QA Team | 2025-12-04 | CORS issue while calling backend APIs from frontend | Sprint 1 | Backend Developer | Configuration | Enabled CORS in Flask backend | 2025-12-05 | Closed | Issue resolved for local setup
2 | QA Team | 2025-12-05 | Login API allows empty username or password | Sprint 1 | Backend Developer | Validation | Added input validation checks | 2025-12-06 | Closed | Handled invalid input
3 | QA Team | 2025-12-06 | Wellness plan markdown not rendering properly in UI | Sprint 2 | Frontend Developer | UI Defect | Integrated react-markdown library | 2025-12-07 | Closed | Proper formatting achieved
4 | QA Team | 2025-12-07 | Follow-up questions lose previous context | Sprint 2 | Backend Developer | Logic Defect | Stored last plan and recommendations in memory | 2025-12-08 | Closed | Context continuity maintained
5 | QA Team | 2025-12-09 | API delay when Groq model response is slow | Sprint 3 | Backend Developer | Performance | Added timeout and error handling | 2025-12-10 | Closed | Improved response stability
6 | QA Team | 2025-12-10 | Application crashes on empty symptom input | Sprint 3 | Backend Developer | Runtime Defect | Added request validation and fallback response | 2025-12-11 | Closed | Prevented application crash